# Stage 2 Drama	Subject Advice and Strategies

## Stage Manager’s Checklist

#### Chronological task list

The checklist below is based on a 12 week production period, with 11 weeks of pre-production and 1 week of performance.

*Discussion/ Communication/Negotiation can include:

verbal discussion substantiated by individual personal notes; written notations (journal, notebook and folder); email.

#### Preparation phase

|  | Read through plays/choose play. |
| --- | --- |
|  | Assist director with preparations e.g. copying scripts. |
|  | Organise an audition schedule. |
|  | Work with the director to create ‘French scenes’ in order to streamline rehearsals. |
|  | Book a rehearsal space. |
|  | Organise a copy of the script for your prompt script. It should be single sided A4. |

#### Week 1 – Reading and Discussion of Text

|  | Establish a production journal, folder or workbook. This needs to be your personal method of record keeping and archiving your process throughout the production period. |
| --- | --- |
|  | As stage manager you are integral in the preparation and operation of each performance. You control all the disparate elements to combine them into a synchronised performance as the director has envisaged. |
|  | Discuss the general themes and ideas contained within the text with the director and ensemble. Examine each character’s words, actions, the stage directions and subtext of the play. Record these ideas in your journal. |
|  | Create a scene breakdown examining each scene and its intention that can be shared and discussed with other offstage members and director. Record the page number each scene starts on so that you can find these in a hurry. Note which characters appear in each scene. |
|  | Discuss rehearsal times; bump in/production week/bump out schedules and general time management of the production with the ensemble and director. |

#### Week 2 - Casting

|  | Discuss with the director their intention for the production and think about how your role will complement this interpretation of the play. This should happen with the offstage team as a group. There may be a lot of new information for you to think through after this meeting. |
| --- | --- |
|  | Research the context of the text, particularly style of production and historical/social/cultural context. The director will no doubt have identified a number of elements for you to investigate when you discussed their intention for the play. |
|  | Compile a list of literal references to props from the stage directions with page numbers so you can refer to them quickly. Discuss this list with the director in order to establish if they wish to use all props listed. Discuss the design of the props with the designer to ensure consistency. |
|  | Develop images/collages/ideations/montages of possible props ideas for the production. |
|  | Collect photos from magazines/internet/video and other visual sources of images of what the props could look like. Share these with the off stage team and the director. |
|  | Create a cast list when auditions are completed. Create a crew list when positions have been decided on. |

#### Week 3 – Exploration rehearsals

|  | Attend rehearsals. |
| --- | --- |
|  | Visit the venue if it is unfamiliar to you and acquire a 1:25 scale plan of the stage. |
|  | Complete a mark-up of the acting space in your rehearsal venue. E.g. are there immovable stairs in the space, a balcony you are using? Is the space proscenium arch, traverse etc.? The set designer will have a large influence on the specifics but there may be some things which are non-negotiable. |
|  | Create a contact list for the ensemble. |
|  | Create a rehearsal schedule with the director. |
|  | Liaise with the offstage and onstage team members. |
|  | Ensure basic ‘necessities’ are provided in the rehearsal space, e.g. toilets, tea and coffee, water, first aid kit and a phone available in an emergency. |
|  | Ensure the rehearsal room is set-up with adequate chairs for the ensemble and a table for yourself which the director may also like to use. |
|  | Establish a series of warm-up exercises for the ensemble with the director. |
|  | Run the warm-up at the start of each rehearsal so that the ensemble is focussed as well as physically and vocally ready for the task. |

#### Week 4 - Exploration rehearsals

|  | Attend rehearsals. |
| --- | --- |
|  | Confirm the booking for the performance space, including bump in and pre-production. |
|  | Create a production week schedule and establish a weekly production meeting time where all off stage team members and the director can meet. |
|  | Create a list of all set, costume, lighting, sound, props etc. references in the script to compare with the off stage team. |
|  | Create ideations of possible prop designs in your journal. |
|  | Continue your discussions of ideas and interpretation with the offstage team. |
|  | Ensure the ensemble understands the director’s intention. |

#### Week 5 – Exploration rehearsals

|  | Attend rehearsals |
| --- | --- |
|  | Gather any rehearsal props, set, costumes that have been decided on for the actors to use, e.g. a period skirt, a walking stick, etc. These will begin to be clarified in the next few weeks. |
|  | Establish if your school has any props that you would be happy to use. |
|  | Liaise with the offstage team as they work to complete their exploration and move into the building phase of the production. Ensure their ideas are complementary with each other and the director’s intention. |
|  | Ensure you participate in regular discussions with the director so that you can efficiently implement their intention during rehearsals. |
|  | Note preliminary blocking in the prompt script. This could change dramatically but could also be a brilliant experiment that without your notation may be lost. |
|  | Liaise with the onstage ensemble as they move from the exploration stage to the building phase of the production. Choices will start to be made and elements solidified. |

#### Week 6 – Building rehearsals

|  | Attend rehearsals |
| --- | --- |
|  | Complete mark-up of the set in the rehearsal space. |
|  | Once the set design has been established create small plans of each set configuration you can copy and stick into your prompt script to record final blocking. |
|  | Finish your props list with documentation and drawings for each item and establish if you are going to borrow, hire make, or buy each item. |
|  | Ensure you have an understanding of all the offstage concepts so that you can clarify any issues for the onstage ensemble during rehearsals. |
|  | Work with crew. |

#### Week 7 - Building rehearsals

|  | Attend rehearsals |
| --- | --- |
|  | As scenes solidify start to time the scenes or Acts. A number of elements such as sound, music, multimedia etc. will find this information very useful. |
|  | Gather/make props. |
|  | Work with crew. |

#### Week 8 - Building rehearsals

|  | Attend rehearsals. |
| --- | --- |
|  | Complete all blocking ready for plotting the lighting. |
|  | Schedule Bump in/Bump out and Production week, particularly rigging, plotting, costume parade, cue to cue rehearsal, tech rehearsal and dress rehearsals in collaboration with the offstage members and crew. |
|  | Gather/ Make props. |
|  | Work with crew. |

#### Week 9 – Polishing rehearsals

|  | Attend rehearsals. |
| --- | --- |
|  | Coordinate the list for program photos. |

#### Week 10 Polishing rehearsals

|  | Meet with the lighting, sound, set and costume designer etc. and record in the prompt script the cue points they have identified. |
| --- | --- |
|  | Gather/ Make props. |
|  | Work with crew. |

Week 11 - Polishing rehearsals

|  | Supervise all elements bumping into the theatre. |
| --- | --- |
|  | Set up the dressing rooms. |
|  | Display a Scene/character breakdown backstage so all actors know when their character is onstage. |
|  | Coordinate the costume parade to check all costumes are finished and work with the lighting colours. |
|  | Set up a props table back stage, by covering a table with paper and tracing around each prop, writing the name inside so they are returned to the correct place. |
|  | Set up an area for any set pieces that may need to come on or off during the show. |
|  | If you need to spike [use small right angled tape marker on the stage] the set pieces so you know where they are on stage. |
|  | Ensure actors have any personal props and negotiate if they need you to preset them for performance. However, they may choose to do this themselves. |
|  | If you plot the lighting when you are not rehearsing, which is the ideal situation, organise a walker for plotting so that the lighting designer can see what the actors will look like onstage. |
|  | Plot the lights and sound adjusting your prompt script if necessary. |
|  | Work with crew. |

#### Week 12 – Production week

|  | Work with crew. |
| --- | --- |
|  | Run a Cue to cue rehearsal. It is often an efficient way to check that each cue works, it also allows you and the operators to get a feel for their jobs and timing. All sound, lighting, mech, multimedia, acting, costume quick change etc. cues need to be run until you are happy. The actors should be involved so that you can time cues by hearing their lines and seeing their actions. Many Stage Managers still like to sit in the auditorium with the director at this point so communication between the two of you is more efficient. |
|  | Run the technical rehearsal from the position you will be calling from in performance. You need to call all cues as you would in performance, however, if you feel a cue has not been completed correctly you need to stop and re run the cue. The director will also let you know if they are unhappy with the cue. |
|  | At the dress rehearsals the production should be running as it would in performance. You will no doubt receive notes from the designers and director about the timing of some cues. Often it’s not a case of something you have not done correctly, but the production coming together as a whole and some refining necessary. |
|  | Ensure you have gathered all the evidence of your process for your interview with the moderator. |
|  | Participate in a ‘mock’ interview with your teacher. |
|  | Performance and interview with the moderator. |
|  | Bump out and supervise the return of any hired equipment. |
|  | Supervise clean-up and storage of all items. |

prepared by Cassandra Backler